Project Management Plan Document

Hospital Management System

Project Name: Hospital Management System

Owning Organization: King Abdulaziz Hospital

Version Number: Version 1.0

Date: November 19, 2025

Prepared by: Noura Mohammed AlKabkabi

Reviewed by: ........................

Approved by: Hani Mayajan

# 1. Executive Summary

## 1.1 System Overview

The Hospital Management System is a comprehensive full-stack web application designed to digitize and streamline all administrative operations and processes at King Abdulaziz Hospital. The system provides a unified platform for managing all aspects of daily hospital operations, including patient management, appointments, staff administration, and medical resources.

## 1.2 Development Objectives

The main objectives of developing this system include:

• Digitize all paper-based administrative forms and requests

• Improve workflow efficiency and reduce transaction processing time

• Minimize human errors from manual data entry

• Provide a centralized, secure, and unified database

• Enhance quality of services provided to patients

• Enable access to information anytime, anywhere

## 1.3 Expected Benefits

• Reduce request processing time by 60%

• Lower operational costs associated with paper-based transactions

• Improve patient experience through easy access to services

• Increase data accuracy and reduce errors

• Improve coordination between different departments

• Enable access to information from anywhere at any time

## 1.4 Key Deliverables

• Integrated web system working on all browsers

• Centralized secure database

• Interactive dashboards for management and staff

• Patient and appointment management application

• Electronic request and approval management system

• Advanced reporting and statistics system

• Comprehensive user guides in Arabic and English

# 2. Document Scope

## 2.1 In Scope

This document covers:

• Comprehensive planning for the Hospital Management System project

• Functional and non-functional requirements for the system

• Project management plan according to PMBOK standards

• Architectural and technical design of the system

• Testing and quality plans

• Deployment and operation plan

• Training and maintenance plans

## 2.2 Out of Scope

This document does not include:

• Detailed technical programming and code specifics

• Detailed user interface designs (UI Mockups)

• Legal contracts and agreements

• Detailed cybersecurity policies for the hospital

• Specialized medical equipment management

# 3. Project Overview

## 3.1 System Concept

The system concept is based on creating a comprehensive electronic platform that connects all departments and administrative operations at King Abdulaziz Hospital. The system targets replacing traditional paper-based forms and transactions with seamless digital processes that ensure speed, efficiency, and accuracy in performance.

## 3.2 Problems Addressed

The system addresses the following challenges:

• Slow processing of paper-based requests and forms

• Difficulty tracking the status of requests and transactions

• Loss or damage of paper documents

• Difficulty accessing historical data

• Repetitive data entry across different systems

• Errors resulting from manual data entry

• Difficulty coordinating between different departments

• Lack of unified and accurate reports

## 3.3 Strategic Goals

• Digital Transformation: Support digital transformation strategy in the healthcare sector

• Operational Efficiency: Improve productivity and reduce costs

• Service Quality: Enhance patient satisfaction levels

• Standards Compliance: Adhere to healthcare quality and accreditation standards

• Decision Making: Provide accurate data to support management decisions

## 3.4 Alignment with Hospital Vision

The project aligns with King Abdulaziz Hospital's vision of being a leading healthcare institution providing high-quality medical services using the latest technologies. The project also supports the goals of Saudi Vision 2030 in digital transformation and improving the quality of healthcare services.

## 3.5 Stakeholders

Key project stakeholders:

| Role | Interest | Type |
| --- | --- | --- |
| Senior Management | Strategic decision-making and performance improvement | Internal |
| Medical Staff | Easy access to medical information | Internal |
| Administrative Staff | Simplify daily work procedures | Internal |
| Patients | Receive faster and better services | External |
| IT Department | System maintenance and management | Internal |
| Regulatory Bodies | Compliance with standards and regulations | External |

# 4. Project Scope

## 4.1 Functional Requirements

### 4.1.1 Patient Management

• Register new patient data

• Update existing patient information

• Search and query patient data

• Manage electronic medical records

• View patient medical history

### 4.1.2 Appointment Management

• Book medical appointments

• Modify and cancel appointments

• Send automatic reminders

• Display doctor schedules

• Manage waiting lists

### 4.1.3 Staff Management

• Register employee data

• Manage permissions and roles

• Track attendance and departure

• Manage schedules and shifts

• Performance evaluation

### 4.1.4 Request and Approval Management

• Create electronic requests (leave, purchases, maintenance)

• Approval workflow

• Track request status

• Automatic notifications

• Archive requests

### 4.1.5 Reports and Statistics

• Department performance reports

• Patient statistical reports

• Financial reports

• Human resources reports

• Export reports in various formats (PDF, Excel)

## 4.2 Non-Functional Requirements

### 4.2.1 Performance

• Page response time: Less than 2 seconds

• Capacity to accommodate 500 concurrent users

• Process 1000 transactions per minute

• System availability: 99.5% uptime

### 4.2.2 Security

• Multi-factor authentication (MFA)

• Data encryption in transit and at rest

• Role-based access control (RBAC)

• Comprehensive audit log for all operations

• Compliance with healthcare data protection standards

### 4.2.3 Scalability

• Ability to add new departments and units

• Support growth in number of users

• Integration capability with external systems

• Scalable architecture

### 4.2.4 Usability

• Easy and intuitive user interface

• Support for Arabic and English languages

• Responsive design working on all devices

• Clear and helpful error messages

• Instant user assistance

## 4.3 Project Boundaries and Constraints

• Project budget is fixed

• First phase must be completed within 8 months

• Integration with legacy systems may be limited

• Must comply with local healthcare standards and regulations

• Intensive staff training may be required

# 5. Project Management Plan

According to PMBOK (Project Management Body of Knowledge) standards

## 5.1 Schedule Management

### 5.1.1 Project Execution Phases

| Phase | Description | Duration | Deliverables |
| --- | --- | --- | --- |
| Phase 1: Initiation & Planning | Requirements analysis and detailed planning | 6 weeks | Requirements document, Project plan |
| Phase 2: Design | System and database design | 4 weeks | Design documents, Prototypes |
| Phase 3: Development | System programming and development | 16 weeks | Programmed system, Code modules |
| Phase 4: Testing | System testing and bug fixing | 4 weeks | Test reports, Certified system |
| Phase 5: Deployment | System deployment and training | 2 weeks | Deployed system, Trained users |
| Phase 6: Operations & Maintenance | Technical support and continuous development | Ongoing | Stable system, Regular updates |

### 5.1.2 Timeline

Total project duration: 32 weeks (approximately 8 months) for the first phase deployment
Expected start date: November 19, 2025
Expected deployment date: July 2026

### 5.1.3 Major Milestones

• M1: Requirements document approval - Week 6

• M2: Architecture design approval - Week 10

• M3: 50% development completion - Week 18

• M4: Full development completion - Week 26

• M5: Acceptance testing passed - Week 30

• M6: Official launch - Week 32

## 5.2 Cost Management

### 5.2.1 Detailed Cost Estimate

A comprehensive cost estimate has been prepared based on project requirements and Saudi market rates for 2025:

### Budget Summary

| Category | Amount (SAR) |
| --- | --- |
| Human Resources | 1,778,000 |
| Infrastructure & Hosting | 265,000 |
| Software Licenses | 102,000 |
| Integration Services | 43,000 |
| Training & Deployment | 155,000 |
| Security & Compliance | 105,000 |
| Contingency Reserve (10%) | 244,800 |
| TOTAL PROJECT BUDGET | 2,692,800 |

** Total Estimated Budget: 2,692,800 Saudi Riyals **

** Approximately: $718,080.00 US Dollars **

### 5.2.2 Budget Breakdown Details

#### A) Human Resources: 1,778,000 SAR

Team of 15 professionals including:
• Project Manager (1): 200,000 SAR
• Business Analysts (2): 288,000 SAR
• UI/UX Designer (1): 90,000 SAR
• Senior Full Stack Developers (2): 352,000 SAR
• Full Stack Developers (3): 384,000 SAR
• QA Engineers (2): 168,000 SAR
• Database Administrator (1): 160,000 SAR
• Security Specialist (1): 88,000 SAR
• Trainers (2): 48,000 SAR

#### B) Infrastructure & Hosting: 265,000 SAR

• Cloud hosting (AWS/Azure) - 1 year: 120,000 SAR
• Managed database services: 60,000 SAR
• Dev/Staging environments: 36,000 SAR
• File storage and CDN: 24,000 SAR
• Backup and disaster recovery: 18,000 SAR
• SSL certificates: 5,000 SAR
• Domain and DNS: 2,000 SAR

#### C) Software Licenses: 102,000 SAR

• Development tools and IDEs: 30,000 SAR
• Project management tools (Jira, Confluence): 15,000 SAR
• Automated testing tools: 25,000 SAR
• Monitoring and APM tools: 20,000 SAR
• Microsoft 365: 12,000 SAR

#### D) Integration Services: 43,000 SAR

• SMS gateway (1 year): 15,000 SAR
• Email service provider: 8,000 SAR
• Payment gateway integration: 20,000 SAR

#### E) Training & Deployment: 155,000 SAR

• Training materials (manuals, videos): 35,000 SAR
• On-site training sessions: 50,000 SAR
• Pilot phase support: 40,000 SAR
• Technical documentation: 30,000 SAR

#### F) Security & Compliance: 105,000 SAR

• Security audit and penetration testing: 45,000 SAR
• Healthcare compliance review: 35,000 SAR
• Encryption solutions: 25,000 SAR

### 5.2.3 Important Budget Notes

• Prices are estimates based on Saudi market rates for 2025

• A 10% contingency reserve is included for risks and unexpected changes

• Human resource costs include salaries only (excluding benefits and insurance)

• Hosting costs are for one year - renewable

• Actual costs may vary based on final specifications and vendor negotiations

• Budget does not include hardware costs (computers, local servers) if applicable

## 5.3 Quality Management

### 5.3.1 Quality Standards

• Compliance with ISO 9001 quality management standards

• Programming standards: Clean Code, SOLID Principles

• Security standards: OWASP Top 10

• Accessibility standards: WCAG 2.1

• Performance standards: Less than 2 seconds page load

### 5.3.2 Testing Methods

• Unit Testing: Test each component separately

• Integration Testing: Test interaction between components

• System Testing: Test the system as a whole

• User Acceptance Testing (UAT): Testing by end users

• Performance Testing: Test speed and load

• Security Testing: Test for security vulnerabilities

### 5.3.3 Quality Assurance Plan

• Code review for all changes

• Automated tests

• Static code analysis

• Periodic quality reviews

• Track and fix discovered bugs

## 5.4 Resource Management

### 5.4.1 Project Team

| Role | Responsibilities | Count |
| --- | --- | --- |
| Project Manager | Planning, monitoring, and coordination | 1 |
| System Analyst | Requirements analysis and documentation | 2 |
| UI/UX Designer | User interface design | 1 |
| Full Stack Developer | Frontend and backend development | 5 |
| Database Engineer | Database design and management | 1 |
| QA Engineer | System testing and quality assurance | 2 |
| Security Specialist | System security assurance | 1 |
| Trainer | User training | 2 |

### 5.4.2 RACI Matrix

R = Responsible (Executes the task)
A = Accountable (Decision maker)
C = Consulted (Provides input)
I = Informed (Kept informed)

| Task | Project Manager | Analyst | Developers | QA | Management |
| --- | --- | --- | --- | --- | --- |
| Requirements Analysis | A | R | C | I | I |
| Design | A | R | C | C | I |
| Development | A | C | R | I | I |
| Testing | A | I | C | R | I |
| Deployment | R | C | C | C | A |

## 5.5 Risk Management

### 5.5.1 Risk List and Analysis

| Risk | Probability | Impact | Rating | Response Plan |
| --- | --- | --- | --- | --- |
| Schedule delay | Medium | High | High | Add resources, reschedule tasks |
| Budget overrun | Medium | Medium | Medium | Strict cost monitoring, approvals before spending |
| Resistance to change | High | Medium | High | Intensive training, change management |
| Technical issues | Medium | High | High | Intensive testing, technical support team |
| Data breach | Low | Very High | High | Apply strict security standards, training |
| Team member loss | Medium | Medium | Medium | Comprehensive documentation, cross-training |

## 5.6 Change Management

### 5.6.1 Change Request Process

1. Submit change request through official form

2. Impact analysis (schedule, cost, quality)

3. Review by change control board

4. Approve or reject with documented reasons

5. Implement approved change

6. Verify change success

7. Update affected documentation

### 5.6.2 Change Approvers

| Change Type | Approver |
| --- | --- |
| Minor changes (no impact on scope/cost/schedule) | Project Manager |
| Medium changes (limited impact) | Change Control Board |
| Major changes (impact on scope/cost/schedule) | Senior Management |

# 6. System Design

## 6.1 System Architecture

The system is based on three-tier architecture:

1. Presentation Layer (Frontend):
   - User interface
   - Responsive web application
   - HTML5, CSS3, JavaScript Framework

2. Business Logic Layer (Backend):
   - Application server
   - Business rules processing
   - RESTful APIs

3. Data Layer:
   - Central database
   - Data storage and retrieval
   - Relational database management system

** See Appendix A for architecture diagrams **

## 6.2 Technology Stack

Frontend:
• Modern framework (React, Vue.js, or Angular)
• HTML5, CSS3, JavaScript
• Bootstrap or Material UI

Backend:
• Node.js with Express framework
• RESTful API Architecture

Database:
• MySQL relational database
• Redis for caching

## 6.3 Database Design

The database contains the following table groups:

• User and permission tables
• Patient tables
• Appointment tables
• Employee tables
• Request tables
• System tables

** See Appendix B for ERD diagram **

## 6.4 Integration

The system integrates with:
• Email system for notifications
• SMS gateway for reminders
• Payment gateway for payments
• Accounting systems for financial data
• Laboratory systems for test results

# 7. Testing Plan

## 7.1 Testing Types

### Unit Testing

Description: Test each component separately
Responsible: Developers
Success Criteria: 80%+ code coverage

### Integration Testing

Description: Test interaction between components
Responsible: QA Team
Success Criteria: All integrations work correctly

### System Testing

Description: Test the system as a whole
Responsible: QA Team
Success Criteria: All functionalities work as expected

### User Acceptance Testing (UAT)

Description: Testing by end users
Responsible: Hospital Staff
Success Criteria: User approval on all features

### Performance Testing

Description: Measure system performance under load
Responsible: QA Team
Success Criteria: Response < 2 sec, 500 concurrent users

### Security Testing

Description: Discover security vulnerabilities
Responsible: Security Team
Success Criteria: No critical or high vulnerabilities

## 7.2 Acceptance Criteria

• All core functionalities work as specified in requirements

• No critical or high-severity bugs

• Minor bugs (if any) are documented and scheduled for fixing

• System response time less than 2 seconds

• System can handle 500 concurrent users

• All security tests passed

• User approval in UAT phase

• Complete documentation available (user guides, technical support)

# 8. Deployment Plan

## 8.1 Environments

### Development Environment

Purpose: Developer testing
Location: Internal/Cloud servers
Access: Development team

### Testing/QA Environment

Purpose: Quality and integration testing
Location: Separate servers
Access: Dev team and QA

### Staging Environment

Purpose: UAT and training
Location: Production replica
Access: End users for testing

### Production Environment

Purpose: Live usage
Location: Secure production servers
Access: All authorized users

## 8.2 Deployment Strategy

Deployment Type: Phased Rollout

Phase 1 (2 weeks): Pilot deployment
  - One or two departments (e.g., Reception)
  - 20-30 users
  - Intensive monitoring and issue resolution

Phase 2 (1 week): Expansion
  - Add 3-4 more departments
  - 50-100 users
  - Apply required improvements

Phase 3: Full deployment
  - All departments
  - All users
  - Full official operation

## 8.3 Rollback Plan

If critical issues occur:

Rollback Triggers:
• Critical errors preventing system use
• Serious security issues
• Data loss
• Unacceptable performance

Rollback Steps:
1. Stop the new system
2. Restore backup
3. Restart old system (if applicable)
4. Notify all users

Required Time: Less than 2 hours

# 9. Training & Operation

## 9.1 Training Plan

### 9.1.1 Target Groups

| Group | Count | Duration | Content |
| --- | --- | --- | --- |
| Senior Management | 5-10 | 1 day | Dashboards, Reports, Decision Making |
| Reception Staff | 20-30 | 2 days | Patient Registration, Appointments |
| Medical Staff | 50-70 | 3 days | Medical Records, Prescriptions, Appointments |
| Administrative Staff | 30-40 | 2 days | Requests, Approvals, Reports |
| IT Department | 5-8 | 5 days | System Admin, Maintenance, Troubleshooting |

### 9.1.2 Training Methods

• Classroom Training: Group training sessions with practical applications

• Hands-on Training: Use of training environment with real-world scenarios

• E-Learning: Training videos and interactive tutorials available anytime

• On-site Support: Direct assistance during the first week of deployment

## 9.2 User Manuals

The following manuals will be provided:

• General User Manual
• Role-specific guides (Reception, Doctor, Admin, Manager)
• Administrator Guide
• Quick Reference Guide

All manuals available in Arabic and English

# 10. Maintenance & Support

## 10.1 Support Levels

| Level | Description | Responsibilities |
| --- | --- | --- |
| Level 1 (L1) Basic Support | First line of support, receive reports | Answer user inquiries, Solve simple problems, Document reports, Escalate complex issues |
| Level 2 (L2) Technical Support | Solve complex technical problems | Analyze technical problems, Fix minor bugs, Database management, Escalate to L3 when needed |
| Level 3 (L3) Advanced Support | Solve complex and critical problems | Fix complex bugs, Develop new solutions, Major system updates, Handle crises |

## 10.2 Service Level Agreement (SLA)

| Priority | Description | Response Time | Resolution Time |
| --- | --- | --- | --- |
| Critical (P1) | System completely down or critical security issue | 15 minutes | 4 hours |
| High (P2) | Problem affects major functionality | 1 hour | 8 hours |
| Medium (P3) | Problem affects some users | 4 hours | 24 hours |
| Low (P4) | Inquiry or enhancement request | 8 hours | 5 business days |

## 10.3 Support Channels

• Ticketing System: Primary method for submitting reports

• Email: support@hospital.sa for non-urgent issues

• Phone: Hotline XXXX-XXX-XXXX available 24/7 for critical issues

• On-site Support: Field visits for complex problems

• Self-Service Portal: Knowledge base, FAQ, tutorial videos

## 10.4 Maintenance

Preventive Maintenance:
• Daily data backups
• Monthly security updates
• Weekly performance checks
• Monthly database cleanup

Scheduled Maintenance Windows:
• Every Saturday 12:00 AM - 4:00 AM
• 48-hour advance notice
• Avoid impact on business hours

# 11. Appendices

## Appendix A: System Diagrams

This appendix contains:
• System Architecture Diagram
• Workflow Diagrams
• Sequence Diagrams
• Use Case Diagrams

** See attached files for diagrams **

## Appendix B: Database Diagrams

This appendix contains:
• Entity Relationship Diagram (ERD)
• Detailed table schema
• Index and constraint list

** See attached files for database diagrams **

## Appendix C: Glossary and Abbreviations

| Term/Abbreviation | Meaning |
| --- | --- |
| PMBOK | Project Management Body of Knowledge |
| UAT | User Acceptance Testing |
| SLA | Service Level Agreement |
| API | Application Programming Interface |
| RACI | Responsible, Accountable, Consulted, Informed |
| ERD | Entity Relationship Diagram |
| QA | Quality Assurance |
| CRUD | Create, Read, Update, Delete |
| UI/UX | User Interface / User Experience |
| RBAC | Role-Based Access Control |
| REST | Representational State Transfer |
| SQL | Structured Query Language |

## Appendix D: References

1. PMI. (2021). A Guide to the Project Management Body of Knowledge (PMBOK® Guide) – Seventh Edition

2. ISO/IEC 25010:2011 - Systems and software Quality Requirements and Evaluation (SQuaRE)

3. OWASP Top Ten - Web Application Security Risks

4. Health Insurance Portability and Accountability Act (HIPAA) - Healthcare Data Protection Standards

5. Saudi Ministry of Health Standards for Electronic Systems

6. ISO 9001:2015 - Quality Management Systems

# Approvals and Sign-offs

By signing this document, the undersigned confirm their agreement with its contents and commitment to executing the project according to the outlined plan.

| Name | Role | Signature | Date |
| --- | --- | --- | --- |
| Noura Mohammed AlKabkabi | Prepared by |  |  |
| ........................ | Reviewed by |  |  |
| Hani Mayajan | Approved by |  |  |

*** END OF DOCUMENT ***

To add Table of Contents: In Microsoft Word, go to References > Table of Contents